## Tasks
task_id | project | assignee | status | priority | estimated_hours | actual_hours | start_date | due_date | sprint | story_points
TASK-001 | Website Redesign | Alice | Done | High | 16 | 14 | 2025-01-06 | 2025-01-17 | Sprint 1 | 8
TASK-002 | Website Redesign | Bob | Done | Medium | 8 | 10 | 2025-01-06 | 2025-01-10 | Sprint 1 | 3
TASK-003 | Website Redesign | Carol | In Progress | High | 24 | 18 | 2025-01-13 | 2025-01-31 | Sprint 2 | 13
TASK-004 | Website Redesign | Alice | Done | Low | 4 | 3 | 2025-01-08 | 2025-01-10 | Sprint 1 | 2
TASK-005 | Website Redesign | Dave | Blocked | High | 12 | 0 | 2025-01-20 | 2025-01-31 | Sprint 2 | 5
TASK-006 | Website Redesign | Eve | To Do | Medium | 6 | 0 | 2025-02-03 | 2025-02-14 | Sprint 3 | 3
TASK-007 | Mobile App | Frank | Done | High | 20 | 22 | 2025-01-06 | 2025-01-17 | Sprint 1 | 8
TASK-008 | Mobile App | Grace | In Progress | Critical | 32 | 28 | 2025-01-13 | 2025-02-07 | Sprint 2 | 13
TASK-009 | Mobile App | Bob | Done | Medium | 10 | 12 | 2025-01-08 | 2025-01-15 | Sprint 1 | 5
TASK-010 | Mobile App | Frank | In Progress | High | 16 | 10 | 2025-01-20 | 2025-02-07 | Sprint 2 | 8
TASK-011 | Mobile App | Henry | To Do | Low | 8 | 0 | 2025-02-10 | 2025-02-21 | Sprint 3 | 3
TASK-012 | Mobile App | Grace | Done | Medium | 12 | 14 | 2025-01-10 | 2025-01-24 | Sprint 1 | 5
TASK-013 | Mobile App | Frank | In Progress | High | 24 | 16 | 2025-01-20 | 2025-02-14 | Sprint 2 | 13
TASK-014 | Data Pipeline | Alice | Done | Critical | 40 | 38 | 2025-01-06 | 2025-01-31 | Sprint 1 | 21
TASK-015 | Data Pipeline | Dave | Done | High | 16 | 18 | 2025-01-08 | 2025-01-17 | Sprint 1 | 8
TASK-016 | Data Pipeline | Henry | To Do | Medium | 8 | 0 | 2025-02-17 | 2025-02-28 | Sprint 3 | 3
TASK-017 | Data Pipeline | Carol | In Progress | Low | 6 | 4 | 2025-01-15 | 2025-01-24 | Sprint 2 | 3
TASK-018 | Data Pipeline | Eve | Done | High | 20 | 22 | 2025-01-10 | 2025-01-24 | Sprint 1 | 8
TASK-019 | Data Pipeline | Alice | Blocked | Critical | 32 | 20 | 2025-01-13 | 2025-02-07 | Sprint 2 | 21
TASK-020 | Data Pipeline | Dave | To Do | Medium | 10 | 0 | 2025-02-03 | 2025-02-14 | Sprint 3 | 5

## Bugs
bug_id | project | severity | status | reported_by | assigned_to | reported_date | resolved_date | resolution_hours
BUG-001 | Website Redesign | Critical | Fixed | QA Team | Alice | 2025-01-15 | 2025-01-16 | 4
BUG-002 | Website Redesign | Major | Fixed | User | Bob | 2025-01-18 | 2025-01-20 | 8
BUG-003 | Website Redesign | Minor | Open | User | Carol | 2025-01-20
BUG-004 | Website Redesign | Major | Fixed | QA Team | Alice | 2025-01-22 | 2025-01-24 | 6
BUG-005 | Website Redesign | Critical | In Progress | Dev | Dave | 2025-01-25
BUG-006 | Mobile App | Minor | Fixed | QA Team | Frank | 2025-01-16 | 2025-01-18 | 3
BUG-007 | Mobile App | Major | Open | User | Grace | 2025-01-19
BUG-008 | Mobile App | Critical | Fixed | QA Team | Frank | 2025-01-21 | 2025-01-23 | 5
BUG-009 | Mobile App | Minor | Wont Fix | User |  | 2025-01-23
BUG-010 | Mobile App | Major | In Progress | Dev | Grace | 2025-01-28
BUG-011 | Data Pipeline | Critical | Open | QA Team | Henry | 2025-01-17
BUG-012 | Data Pipeline | Major | Fixed | User | Alice | 2025-01-20 | 2025-01-22 | 4
BUG-013 | Data Pipeline | Minor | Open | Dev | Dave | 2025-01-22
BUG-014 | Data Pipeline | Major | In Progress | QA Team | Carol | 2025-01-26
BUG-015 | Data Pipeline | Minor | Fixed | Dev | Eve | 2025-01-12 | 2025-01-14 | 2